## Jira Backlogs
Task ID | Epic | User Story / Task | Description | Story Points | Assigned Team Member | Branch Name | Priority | Status
QA-0 | Project Documentation | Create Project Documentation | Create SRS, JIRA Task Sheet, Presentation, Final Report | 4 | Pawan Sharma | document-setup | High | InProgress
QA-1 | Project Setup | Initialize Flask Project | Set up Flask project structure and virtual environment | 3 | Pranjal | feature/project-setup | High | To Do
QA-2 | Model Integration | Integrate BERT Model | Load fine-tuned BERT model using HuggingFace Transformers | 8 | Amit Kumar | feature/bert-integration | High | To Do
QA-3 | Frontend Development | Design Input Form UI | Create HTML form for context and question input | 5 | Neha Singh | feature/ui-form | Medium | To Do
QA-4 | Backend Logic | Implement Prediction API | Create Flask route for question answering prediction | 8 | Rahul Verma | feature/prediction-api | High | To Do
QA-5 | Validation | Add Input Validation | Validate empty fields and incorrect inputs | 3 | Pawan Sharma | feature/input-validation | Medium | To Do
QA-6 | Testing | Unit Testing for Model | Write test cases for model inference and API | 5 | Anjali Mehta | feature/unit-testing | Medium | To Do
QA-7 | Deployment | Prepare Deployment Files | Create requirements.txt and Procfile for Render deployment | 3 | Amit Kumar | feature/deployment-config | High | To Do
QA-8 | Deployment | Deploy to Render | Connect GitHub repo and deploy web service on Render | 5 | Rahul Verma | feature/render-deployment | High | To Do
QA-9 | Enhancement | Optimize Model Performance | Improve inference time and memory usage | 8 | Neha Singh | feature/model-optimization | Low | Backlog
QA-10 | Documentation | Create Project Documentation | Prepare SRS, README, and deployment guide | 3 | Pawan Sharma | feature/documentation | Medium | To Do